## Sheet1
| Week | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28
| Work Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140
Cost and Schadule management | bar: 1 to 7
Task Management | bar: 7 to 15
1.1 | Risk Management | bar: 16 to 21
Time Management | bar: 16 to 21
Fcality Management | bar: 20 to 29
Project Manager | bar: 20 to 30
Technical Planning | bar: 31 to 35
Requirements Definition | bar: 31 to 32; 36 to 40
1.2 | System Requirements Defintion | bar: 40 to 48
Technical Supervision | bar: 45 to 56
Use Case Design | bar: 57 to 66
1.2.1 | Class Diagram | bar: 63 to 70
Activity Diagram | bar: 63 to 70
Sequence Diagram | bar: 67 to 72
1.2.2 | Unit Coding | bar: 71 to 77
unit Debugging | bar: 72 to 79
Modules System Testing | bar: 81 to 87
1.3 | system integration testing | bar: 83 to 89
Defect Classification Tracking and Befrico | bar: 83 to 89
Acceptance testing | bar: 85 to 91
Sub system testing | bar: 92 to 105
system integration testing | bar: 92 to 105
1.4 | Acceptance testing | bar: 105 to 112
Defect Classification and tracking | bar: 106 to 114
configuration management | bar: 115 to 122
Quality assurance | bar: 115 to 124
1.5 | Development tools and unites | bar: 118 to 126
Team technical training | bar: 120 to 128
Installation planning | bar: 129 to 135
User Support Documentation | bar: 132 to 138
1.6 | Installation management and Coordination | bar: 129 to 140
Installation testing and verification | bar: 129 to 140
Installation performance monitoring | bar: 133 to 140